## Document Information
Field | Details
Project Name | Demo Web Shop E-Commerce Testing
Application Name | Demo Web Shop
Document Name | Test Plan
Document ID | TP-DWS-001
Version | 1.0
Date | 02-09-2026
Prepared By | Senior QA Engineer
Reviewed By | QA Lead
Approved By | Test Manager
Document Status | Draft

## Revision History
Version | Date | Author | Description of Change | Reviewer | Approval
1.0 | 02-09-2026 | Senior QA Engineer | Initial Test Plan for Demo Web Shop | QA Lead | Test Manager

## Project Overview
Section | Details
Project Description | Demo Web Shop is a sample e-commerce platform developed by Tricentis that allows users to register accounts, browse product categories, search products, add items to cart, perform checkout operations, complete payment using credit card information and place orders online.
Business Objective | Ensure customers can register, login, search products, review product details, add products to cart, complete checkout, submit billing and shipping info, complete payment and generate successful order confirmation.
Testing Objective | Verify registration, login/logout, search, cart, checkout, payment and order confirmation with no major regressions.

## Application Overview
Module | Description
Registration | Create customer account
Login | Authenticate existing users
Product Search | Search products from catalog
Product Details | Product information pricing and availability
Shopping Cart | Manage selected products
Billing Address | Capture billing information
Shipping Address | Capture shipping information
Payment Method | Select preferred payment type
Credit Card Payment | Submit payment details
Order Confirmation | Verify successful order placement

## In Scope
Module | Features
Registration | New User Registration; Mandatory Field Validation; Unique Email Validation; Password and Confirm Password Validation; Registration Success Message
Login | Valid Login; Invalid Login; Empty Credentials Validation; Logout Functionality; Remember Me Function
Product Search | Search Existing Product; Search Non Existing Product; Partial Keyword Search; Search Result Accuracy; Search with Special Characters
Product Details | Product Name Verification; Product Price Validation; Product Description Display; Product Image Display; Product Availability Status
Add To Cart | Add Product To Cart; Add Multiple Products; Cart Quantity Update; Cart Counter Update; Duplicate Product Handling
Shopping Cart | View Cart; Update Quantity; Remove Product; Calculate Subtotal; Calculate Total Amount
Billing Address | Existing Address Selection; New Billing Address Entry; Mandatory Field Validation; Country State Selection
Shipping Address | Ship To Same Address; Different Shipping Address; Address Validation
Payment Method | Select Credit Card Payment; Payment Method Navigation; Payment Method Persistence
Credit Card Payment | Cardholder Name Validation; Card Number Validation; Expiration Date Validation; Card Code Validation; Successful Payment Submission
Order Confirmation | Order Review; Order Confirmation Message; Order Number Generation; Thank You Page Verification

## Out of Scope
Feature | Reason
Admin Management Portal | Not accessible in current release
Backend Inventory Services | Internal system
Payment Gateway Internal Processing | Third-party integration
Performance Benchmark Certification | Separate testing stream
Penetration Testing | Security Team Scope
Mobile Native Application | Not part of Demo Web Shop

## Test Items
Test Item | Description | Version
Customer Registration | User account creation workflows | Current
Authentication | Login and Logout services | Current
Product Catalog | Search and Product Details | Current
Cart Services | Add Remove Products | Current
Checkout Services | Billing Shipping Workflow | Current
Payment Processing | Credit Card Payment Module | Current
Order Processing | Order Placement & Confirmation | Current

## Testing Types
Category | Type
Functional | Smoke Testing
Functional | System Testing
Functional | Integration Testing
Functional | Regression Testing
Functional | End-to-End Testing
Non Functional | Usability Testing
Non Functional | Compatibility Testing
Non Functional | Accessibility Testing
Non Functional | Reliability Testing
Other | UI Testing
Other | Negative Testing
Other | Exploratory Testing
Other | Responsive Testing

## Test Strategy
Priority | Module
P1 | Registration
P1 | Login
P1 | Add To Cart
P1 | Billing Address
P1 | Shipping Address
P1 | Payment
P1 | Order Confirmation
P2 | Product Search
P2 | Product Details
P2 | Shopping Cart

## Environment
Environment | Details
Environment | QA
Application URL | https://demowebshop.tricentis.com
OS | Windows 11
Browsers | Chrome Edge Firefox
Mobile Testing | Responsive Browser Testing
Database | SQL Server
Internet | Stable Broadband Connection

## Test Data
Data Type | Description | Example
Valid User | New User Registration | qa_test_001@test.com
Existing User | Registered User | existinguser@test.com
Invalid Email | Invalid Format | usergmail.com
Valid Password | Accepted Value | Test@123
Weak Password | Negative Testing | 12345
Existing Product | Search Testing | Health Book
Existing Product | Search Testing | Laptop
Credit Card | Test Data | Visa 4111111111111111
Expired Card | Negative Validation | 01/2023
Invalid CVV | Negative Validation | 12

## Requirements RTM
Requirement ID | Requirement
REQ-001 | Registration
REQ-002 | Login
REQ-003 | Product Search
REQ-011 | Order Confirmation

## Entry Criteria
Criteria
Requirements are approved
Test plan is reviewed and approved
QA environment is available
Required build is deployed successfully
Test data is prepared
Test cases are reviewed
Required access permissions are granted
APIs and dependent services are available

## Exit Criteria
Criteria
100% planned test cases are executed
95% or greater test case pass rate achieved
No Critical defects remain open
No unresolved blocker defects exist
High-priority defects are resolved or accepted
Regression testing is completed successfully
Traceability matrix is updated
Test summary report is completed
Stakeholder sign-off is received

## Defect Management
Severity | Description
Critical | Checkout or payment unavailable
High | Major business functionality impacted
Medium | Partial functionality affected
Low | Cosmetic or minor issue

## Roles Responsibilities
Role | Responsibility
Test Manager | Test planning monitoring reporting approvals
QA Lead | Strategy creation review execution supervision
QA Engineer | Test case creation execution defect reporting
Automation Engineer | Automation framework development and maintenance
Developer | Defect analysis and bug fixes
Business Analyst | Requirement clarification
Product Owner | UAT validation and acceptance
DevOps Engineer | Environment setup and deployment support

## Tools
Purpose | Tool
Test Management | Jira Xray Azure DevOps
Automation | Selenium Playwright Cypress
API Testing | Postman REST Assured
Defect Tracking | Jira
Performance Testing | JMeter
Database Testing | SQL Server Management Studio
CI/CD | Jenkins Azure DevOps
Version Control | Git GitHub

## Resource Estimation
Role | Resources | Effort
Test Manager | 1 | 2 Days
QA Lead | 1 | 3 Days
Manual QA | 2 | 10 Days
Automation QA | 1 | 5 Days
Total Estimated Effort |  | 20 Person Days

## Deliverables
Deliverable
Test Plan
Test Scenarios
Test Cases
RTM
Test Data Sheet
Defect Reports
Daily Status Reports
Automation Scripts
Regression Report
Test Summary Report
Sign-Off Document

## Timeline
Activity | Duration
Requirement Analysis | 1 Day
Test Planning | 1 Day
Test Case Design | 3 Days
Test Data Preparation | 1 Day
Test Execution | 5 Days
Defect Retesting | 2 Days
Regression Testing | 2 Days
Test Closure | 1 Day

## Risks Mitigation
Risk | Impact | Mitigation
Registration emails not generated | High | Validate DB record creation
Test user accounts reused | Medium | Generate unique emails dynamically
Payment flow unavailable | Critical | Execute payment testing early
Unstable environment | High | Smoke test every deployment
Product data changes | Medium | Maintain baseline product dataset
Browser compatibility defects | Medium | Execute daily cross-browser runs
Order creation failures | Critical | Continuous E2E validation

## Approvals
Stakeholder | Role | Approval Status
QA Lead | Reviewer | Pending
Test Manager | Approver | Pending
Product Owner | Business Approval | Pending
Development Lead | Technical Approval | Pending